## Change Register
Change ID | Change Date | Requested By | System | Change Description | Change Type | Risk Level | Business Impact | Approval Status | Testing Status | Implementation Status | Validation Status | Rollback Plan | Change Owner | Overall Status
CHG-001 | 2026-09-02 | IT Administrator | Microsoft 365 | Enable MFA for remaining users | Normal | High | Medium | Approved | Completed | Completed | Completed | Disable configuration change | IT Manager | Closed
CHG-002 | 2026-09-05 | Cloud Engineer | AWS EC2 | Apply critical security patches | Emergency | High | High | Approved | Completed | Completed | Completed | Restore previous instance configuration | Cloud Security Lead | Closed
CHG-003 | 2026-09-08 | Application Developer | Customer Portal | Deploy application update | Normal | High | High | Approved | Completed | Completed | Pending | Restore previous application version | Application Manager | In Progress
CHG-004 | 2026-09-10 | Network Administrator | Firewall | Update firewall rules | Normal | Medium | Medium | Approved | Completed | Completed | Completed | Restore previous firewall configuration | Network Manager | Closed
CHG-005 | 2026-09-12 | IT Administrator | Employee Laptops | Deploy endpoint security update | Standard | Low | Low | Approved | Completed | Completed | Completed | Reinstall previous version | Endpoint Administrator | Closed
CHG-006 | 2026-09-15 | Infrastructure Manager | Backup Server | Modify backup schedule | Normal | Medium | High | Pending | Pending | Not Started | Not Started | Restore previous schedule | Infrastructure Manager | Open
CHG-007 | 2026-09-18 | Security Engineer | SIEM | Add authentication monitoring rule | Normal | Medium | Medium | Approved | Completed | Completed | Completed | Remove monitoring rule | Security Manager | Closed
CHG-008 | 2026-09-20 | Application Developer | Customer Portal | Database schema modification | Normal | High | High | Approved | In Progress | Not Started | Not Started | Restore database backup | Application Manager | Open

## Change Dashboard
Change Management Dashboard
Total Changes | 8
Standard Changes | 1
Normal Changes | 6
Emergency Changes | 1
High-Risk Changes | 4
Open Changes | 2
In Progress | 1
Closed Changes | 5

## Approval Log
Change ID | Approver | Role | Decision | Approval Date | Comments
CHG-001 | IT Manager | IT Management | Approved | 2026-09-02 | MFA deployment approved
CHG-002 | Cloud Security Lead | Security | Approved | 2026-09-05 | Emergency patch approved
CHG-003 | Application Manager | Application Management | Approved | 2026-09-08 | Application testing completed
CHG-004 | Network Manager | Network Management | Approved | 2026-09-10 | Firewall change approved
CHG-005 | Endpoint Administrator | IT | Approved | 2026-09-12 | Endpoint update approved
CHG-006 | Infrastructure Manager | Infrastructure | Pending |  | Awaiting review
CHG-007 | Security Manager | Security | Approved | 2026-09-18 | Monitoring rule approved
CHG-008 | Application Manager | Application Management | Approved | 2026-09-20 | Database change approved

## Change Testing
Change ID | Test Environment | Test Performed | Test Result | Tester | Test Date | Issues Identified | Retest Required
CHG-001 | Test Tenant | MFA authentication test | Passed | Security Analyst | 2026-09-02 | None | No
CHG-003 | QA Environment | Application functionality test | Passed | QA Analyst | 2026-09-08 | None | No
CHG-004 | Network Test Environment | Firewall rule validation | Passed | Network Engineer | 2026-09-10 | None | No
CHG-006 | Test Environment | Backup schedule test | Pending | Infrastructure Analyst |  | Pending | Yes
CHG-008 | Development Environment | Database schema validation | In Progress | Application Developer | 2026-09-20 | Validation ongoing | Yes