## Sheet1
Risk ID | Risk Name | Asset | Risk Owner | Likelihood | Impact | Risk Score | Risk Level | Mitigation Strategy | Status | Target Completion Date
R-001 | Phishing Attack | Microsoft 365 | IT Manager | 5 | 5 | 25 | High | Enable MFA and phishing training | Open | 2026-08-31
R-002 | SQL Injection | Customer Portal | Application Manager | 4 | 5 | 20 | High | Secure coding and penetration testing | Open | 2026-09-15
R-003 | Malware Infection | Employee Laptops | Endpoint Administrator | 4 | 4 | 16 | High | Update antivirus and patch systems | In Progress | 2026-08-20
R-004 | Ransomware | AWS Servers | Cloud Security Lead | 3 | 5 | 15 | High | Offline backups and EDR | Open | 2026-09-30
R-005 | Insider Threat | HR Database | HR Director | 3 | 5 | 15 | High | RBAC and access reviews | Open | 2026-08-31
R-006 | Credential Theft | VPN Gateway | Network Administrator | 5 | 4 | 20 | High | Strong passwords and MFA | Open | 2026-08-15
R-007 | Firewall Misconfiguration | Firewall | Network Team | 3 | 3 | 9 | Medium | Monthly firewall audits | In Progress | 2026-09-01
R-008 | Backup Failure | Backup Server | Infrastructure Manager | 2 | 4 | 8 | Medium | Test backups quarterly | Open | 2026-09-20
R-009 | Privilege Escalation | Active Directory | Identity Administrator | 4 | 5 | 20 | High | Implement PAM and least privilege | Open | 2026-10-01
R-010 | Data Breach | Finance Database | Finance Manager | 2 | 5 | 10 | Medium | Encrypt sensitive data | Open | 2026-09-10

## Dashboard
Metric | Value
Total Risks | 10
High Risks | 7
Medium Risks | 3
Low Risks | 0
Open Risks | 8
Risks In Progress | 2
Closed Risks | 0